## Sheet1
Student Behaviour Analysis |  |  | Group 1
Change Log
Change ID | Category | Description of Change | Submitted by | Submission Date | Status | Disposition
CHG0001 | Scope | Change was made to focus on only students from Zekelmann School of IT | Project Manager | 09/27/2023 | Approved | Implemented
CHG0002 | Promotion | Flyer promotion by sticking posters on the wall showing it on TV was terminated | Research & Development | 10/29/2023 | Approved | Implemented
CHG0003 | Requirements | Modifying the survey questions | Developer | 10/29/2023 | Approved | Implemented
CHG0004 | Schedule | Extension of the EDA due to insufficient responses. | Subject Matter Expert | 11/22/2023 | Approved | Implemented