## Sheet1
LESSONS LEARNED LOG
Group 1 | Archit Navadiya (0815897)
Dhrumil Patel (0813662)
Felix Saji (0803791)
Arbaz Shaikh (0823127)
Bhumit Navadiya (0812548)
Project Name: |  | Student Behavior Analysis
Project Manager Name: |  | Archit Navadiya
Project Description: |  | Analysis based on an online survey conducted for students' experience and behavior in Zekelman School of IT in St Clair College.
ID | Date Identified | Subject | Situation | Recommendations & Comments
1 | 2023-09-26 | Survey Update | Initial survey design required adjustments suggested by the professor. | The survey needs more information about why we are taking this survey, who is going to use these details, and about the privacy of data.
2 | 2023-10-03 | Survey Promotion | Initial promotion on Blackboard yielded minimal responses, prompting the need for a more engaging promotional strategy. | Develop visually appealing and informative flyers for wider visibility to increase survey participation.
3 | 2023-10-17 | Promoting on notice board | The plan to post on notice boards required ethical approval, potentially causing delays in the project timeline. | Factor in the need for ethical approvals early in the planning stage to prevent unforeseen delays.
4 | 2023-11-09 | Reposting survey | To get more survey responses we planned to repost on Blackboard | After dropping to post it on the notice board we decided to repost it on Blackboard for more responses and we almost doubled our responses.
5 | 2023-11-23 | Data cleaning | Data cleaning and analysis are crucial for meaningful insights and effective dashboard creation. | While cleaning our data we faced several problems as people misspelled province names, in the sector section they have written subfield, not the sector. We learned to give them examples or options for that instead of giving them textbox.
Note on A11: • ID: A unique ID number used to identify the lesson learned in the lesson learned log.
Note on B11: • Date Identified: This column should be populated with the date that the lesson learned was identified.
Note on C11: • Subject: This column should be populated with a brief attention grabbing headline that describes the subject of the lesson learned.
Note on D11: • Situation: This column should be populated with a detailed description of the situation learned from.
Note on E11: • Lesson Learned & Recommendations: This column should be populated with a description of the lesson learned from the situation described in column E and the corrective action taken. Include recommendations regarding the outcome of the corrective action, good or bad, to help guide future project managers.